ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

Clinical hospital “Dr.Trifun Panovski” Bitola

## Country background

Republic of North Macedonia as a candidate country for membership in the European Union is erected before the challenges of the efficient implementation of serious reforms in the many sectors including health services to the citizens. Main cross-border challenges to be tackled Teleheartgurad project is to significantly improve access to and quality of healthcare services for cardiovascular patients in the recovery phase after an acute coronary syndrome in

the cross-border area.

## Current situation in the sector

- Health systems in Europe are at the core of its high level of social protection and they are a cornerstone of the European social market economy. The problems caused by the economic crisis, coupled with more structural changes in demography and the cardiovascular diseases affecting populations in Europe,and in our cross-borde region as well, reinforce the necessity to reform and modernize those systems.This objective in our project is planned to be achieved through integrated telemonitoring services, the use of wearable devices,the development of a unified digital platform, and the adoption of modern care protocols.

- Thus, the Project aims to further relieve the public health system of both countries, while simultaneously upgrading healthcare services through modern monitoring protocols and the use of advanced, stateof-the-art health technologies.

## Related programmes and other donor activities

NA

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is :

The purpose of the contract is to ensure overall

technical and administrative

management of the Act, in close cooperation with the

Internal Project team, so as to ensure

smooth implementation, delivery of deliverables,

financial discipline, and full compliance with the

Programme regulations.

## Specific objective(s)

The  specific objective (Outcome) of this contract is as follows:

Work on  administration and technical part during the whole time of the project

such as screening of the target group of patients,following them,reports for the project progress to the LB,finance administration (tenders,payments,final bills),working on the MIS,working on preparation of the opening event etc.

## Expected outputs to be achieved by the contractor

The service will be paid according staff flat rate 12% from the realized purchases(equipment and external). Payment(s) is/are based on the approval of this/these deliverable(s). The main expected outputs of this contract are as follows:

1. Preparation of required material and presentations

for disemniation event and project team meeting.

2.Transalte the common developed protocol by the medical staff of all partners, in the native language.

3.Preparation of two seminars for acquiring new skills in the field of medical care among medical and rescue staff in the Programme area which will improve its quality and  may translate into its effectiveness in the treatment of cardiovascular diseases. Each seminar should be addressed to 60 healthcare professionals.

4. Preparation of financial reports,preparing documentation from the hospital.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Clear and full understanding of the contract objectives and purposes on behalf of the Contractor.

## Risks

The main risk attached to the assignment is the critical time schedule. The Contractor shall therefore take all necessary actions to avoid delays, and any potential delays shall be brought to the immediate attention of the Contracting authority so that corrective actions may be implemented.

# SCOPE OF THE WORK

## General

### Description of the assignment

For the effective implementation of the Project, an experienced staff

will be contracted to support the Contracting Authority in

implementation of  the whole project. Three of them will work as a team together

with the Interal Project team,each member in the field of her/his best skills.

### Geographical area to be covered

CBC regions of Republic of North Macedonia and Greece

### Target groups

Patients with Cardiovascular diseases.

## Specific work

The Project focuses on activities that add measurable

value in the cross-border region:

• Management & coordination (WP1):

Establishment of a Joint Administrative Unit and

Steering Committee, overall coordination by an

independent Overall Project Manager; implementation

of an Internal Communication Plan and maintenance

of reporting procedures.

• Communication & publicity (WP2): Development

of corporate identity, website, multichannel ecampaigns,

and public information/dissemination

events.

• Equipment & infrastructure (WP3): Upgrade of 4

cardiology clinics with monitoring equipment,

procurement of 60 wearables for 24/7 telemonitoring,

and development of a Unified Patient Data Platform

for in-hospital and out-of-hospital care.

• Training & skills (WP4): Skills upgrade of 10

physicians in e-Health & protocol evaluation,

reskilling of 50 healthcare professionals, and training

of 200 local physicians in managing cardiovascular

cases using digital tools.

• Networking & knowledge transfer (WP5):

Organisation of an innovation demonstration

roundtable with 20 hospitals, “engagement days” for

health professionals, and development of 2 joint

protocols (emergency & clinical cardiology) to

harmonize practices in the cross-border area.

Key deliverables/outputs:

4 upgraded clinics; 1 unified data platform; 60

wearables; 2 joint protocols; training/reskilling of 60

professionals and briefing of 200 physicians; 1

roundtable with 20 hospitals.

The Contractor must also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project.

## Project management

### Responsible body

The Contracting Authority for the contract is:

Public Health Institution Clinical Hospital Bitola

### Management structure

Internal project team previously defined,can make decisions for all project activities under supervision of the Director of Contracting authority,and signed from Director too.

### Facilities to be provided by the contracting authority and/or other parties

The Contracting Authority shall supply the Contractor promptly with any useful information and documentation which may be relevant to the performance of the contract.

# LOGISTICS AND TIMING

## Location

The location of the project is in Republic of North Macedonia and in the Republic of Greece. The Contractor should be able to conduct activities in the territory of the Municipality of  Bitola,and  from home-based location,and by e-mail correspodentation depending on activity.

## Start date & period of implementation of tasks

The intended start date is 3.11.2025 and the period of implementation of the contract will be 22 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Personnel

All staff candidates should have experience with the Projects financed from the international organizations,and/or have medical education,and/or have experience within finance and accounting,and/or very good knowing of English language.

### Experts

### Support facilities & backstopping

## Office accommodation

Office accommodation for each staff member providing input to the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall be well equipped with office items.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the report  before every planned payment from the Contracting Authority depending of the activities.

## Submission and approval of reports

The report referred to above must be submitted to the project coordinator identified in the contract. The project coordinator is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Annual users of new or modernised e-health care services

Annual users of new or modernised health care facilities

## Special requirements

NA

* * *